## Bepanthen DX8 Assembly
Issue key | Summary | Planned start | Planned End | Actual Start | Actual End | Current status | Owner
WSFD-2960 | ProductListing | 2020-01-29 | 2020-01-30 |  |  | In progress | Radhika and Tomson
WSFD-2968 | ProductListing - Baby Sun Care | 2020-02-10 | 2020-02-10 |  |  | Yet to start | Radhika and Tomson
WSFD-2967 | ProductListing - Baby and mother | 2020-02-10 | 2020-02-10 |  |  | Yet to start | Radhika and Tomson
WSFD-2966 | ProductListing - Bepanthen's range | 2020-02-10 | 2020-02-10 |  |  | Yet to start | Radhika and Tomson
WSFD-2959 | PageWithTabs - Nappy rash | 2020-02-10 | 2020-02-10 |  |  | Yet to start | Radhika and Tomson
WSFD-2955 | CategoriesLP | 2020-01-27 | 2020-01-28 |  |  | In progress | Radhika and Tomson | Need custom style. Ticket raised
WSFD-2958 | CategoriesLP - Your babyâ€™s skin | 2020-01-28 | 2020-01-28 |  |  | on hold | Radhika and Tomson | Dependency on custom style
WSFD-2957 | CategoriesLP - Understanding your skin | 2020-01-28 | 2020-01-28 |  |  | on hold | Radhika and Tomson | Dependency on custom style
WSFD-2925 | Article Page | 2020-01-28 | 2020-01-29 |  |  | In progress | Radhika and Tomson | Need custom style. Ticket raised
WSFD-2939 | Article Page - Learning module | 2020-02-06 | 2020-02-06 |  |  | Yet to start | Radhika and Tomson
WSFD-2938 | Article Page - About Bepanthen globally | 2020-02-06 | 2020-02-06 |  |  | Yet to start | Radhika and Tomson
WSFD-2937 | Article Page - Skin irritations in babies | 2020-02-06 | 2020-02-06 |  |  | Yet to start | Radhika and Tomson
WSFD-2936 | Article Page - Can teething cause nappy rash? | 2020-02-06 | 2020-02-06 |  |  | Yet to start | Radhika and Tomson
WSFD-2935 | Article Page - Learn about nappy rash | 2020-02-06 | 2020-02-06 |  |  | Yet to start | Radhika and Tomson
WSFD-2934 | Article Page - Stretch marks | 2020-02-06 | 2020-02-06 |  |  | Yet to start | Radhika and Tomson
WSFD-2932 | Article Page - Preventing the development of stretch marks | 2020-02-06 | 2020-02-06 |  |  | Yet to start | Radhika and Tomson
WSFD-2930 | Article Page - Your skin's structure | 2020-02-06 | 2020-02-06 |  |  | Yet to start | Radhika and Tomson